## Sheet1
Development programs for the year 2021
Divisional Secretariat -: Badalkumbura
2021.08.02
Serial number | Ministry | Program | Total number of projects | Number of approved projects | Approved Allocation Amount (Rs.) | Allocation received (Rs.) | Physical progress | [5 empty] | Progress as at 02.08.2021
[7 empty] | 0-10% | 11-25% | 26-50% | 51-75% | 76-99% | 100%
1 |  | Back to Village Development Program with “Chat with the Village” project | [10 empty] | Project proposals obtained by the Rural Steering Committees are incorporated into the computer database.
2 |  | Rural Road Development Program | 73 | [9 empty] | Referred to the Ministry
3 |  | Saubhagya Production Village Program | 1 | 1 |  |  | 1 | [5 empty] | The plan for the shade house and water system has been requested from the Office of the Deputy Director of Agriculture
4 |  | Program to create one Rural Industrial Entrepreneur per Grama Niladhari Division | 41 | [9 empty] | The list of selected entrepreneurs has been sent to the District Secretariat
5 | State Ministry of Rural and School Sports Infrastructure Development | Development of rural sports grounds | 1 | 1 | 1470000 | [6 empty] | 1 | Finished work
6 |  | Decentralized budget program | 81 | 47 | 7915500 |  | 81 | 12
7 | Ministry of Buddhasasana, Religious and Cultural Affairs | Sustainable Punyagrama Program | 2 | 2 | 299960 |  | 1 | 1 |  |  |  |  | Agreed
|  | Improvement of underdeveloped Dhamma schools | 3 | 3 | 750000 |  |  | 3 |  |  |  |  | Agreed
|  | Improvement of underdeveloped temples | 2 | 2 | 500000 |  |  | 1 |  |  |  |  | Agreed
Total |  |  | 204 | 56 | 10935460 | 0 | 83 | 17 | 0 | 0 | 0 | 1